## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint1 | Sprint1 | US -01 | Create Spring Boot project and configure MySQL | MUST HAVE | NA | Dharanish | 3- Completed
Sprint1 | Sprint1 | US-02 | Design Account entity with account no,balance | MUST HAVE | US-01 | Dharanish | 3- Completed
Sprint1 | Sprint1 | US -03 | Implement Account Repository using JPA | MUST HAVE | US-02 | Dharanish | 3- Completed
Sprint1 | Sprint1 | US-04 | Implement Add Account REST API | MUST HAVE | US-03 | Dharanish | 3- Completed
Sprint1 | Sprint1 | US -05 | Implement View Account and View All Accounts APIs | SHOULD HAVE | US-04 | Dharanish | 3- Completed
Sprint 2 | Sprint2 | US-06 | Implement Deposit operation and balance update logic | MUST HAVE | US-05 | Dharanish | 3- Completed
Sprint 2 | Sprint2 | US-07 | Implement Withdrawal operation with balance validation | MUST HAVE | US-06 | Dharanish | 3- Completed
Sprint 2 | Sprint2 | US-08 | Implement Money Transfer between two accounts | MUST HAVE | US-07 | Dharanish | 3- Completed
Sprint3 | Sprint3 | US-09 | Implement low balance detection logic | MUST HAVE | US-07 | Dharanish | 3- Completed
Sprint3 | Sprint3 | US-10 | Implement email alert for low balance | MUST HAVE | US-09 | Dharanish | 3- Completed
Sprint3 | Sprint3 | US-11 | Generate CSV file report for account and transaction data | SHOULD HAVE | US-08 | Dharanish | 3- Completed
Sprint4 | Sprint4 | US-12 | Create simple frontend pages for account operations | COULD HAVE | US-05 | Dharanish | 3- Completed
Sprint4 | Sprint4 | US-13 | Create frontend pages for transaction operations | COULD HAVE | US-08 | Dharanish | 3- Completed
Sprint4 | Sprint4 | US-14 | Perform integration testing of all modules | COULD HAVE | US-13 | Dharanish | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 71 | 23 | 23 | 17 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Project setup & MySQL configuration | 2025-01-12 | 2025-01-12 | Dharanish | SETUP | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Account entity & repository design | 2025-02-12 | 2025-04-12 | Dharanish | Coding | 3- Completed | 8 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Add / View account REST APIs | 2025-04-12 | 2025-08-12 | Dharanish | Coding | 3- Completed | 10 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-04 | Account,Transfer Controller | 2025-09-12 | 2025-12-12 | Dharanish | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-05 | Implement account number auto-generation | 13/12/2025 | 14/12/2025 | Dharanish | Coding | 3- Completed | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-06 | Transaction module (deposit, withdraw, transfer) | 15/12/2025 | 18-12-2025 | Dharanish | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-07 | Low balance email alert | 19/12/2025 | 23/12/2025 | Dharanish | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-08 | CSV file report generation | 24/12/2025 | 25/12/2025 | Dharanish | Coding | 3- Completed | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-09 | Exception handling and input validation | 26/12/2025 | 27/12/2025 | Dharanish | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-10 | UI form validation in frontend | 23/12/2025 | 24/12//2025 | Dharanish | Design | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-11 | Frontend integration & testing | 25/12/2025 | 28/12/2025 | Dharanish | Integration Test | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | DAY1 | MySQL connection error | error Fixed DB URL and added correct MySQL dependency
Sprint 1 | Day 4 | API returning null values | Debugged service layer and fixed repository
Sprint 2 | Day 7 | Deposit API not updating balance | Corrected service logic
Sprint 2 | Day 19 | Withdraw validation missing | Added balance validation
Sprint 2 | Day 10 | Table not creating in DB | DB Fixed Hibernate ddl-auto config
Sprint 2 | Day 13 | Deposit logic error | Corrected service method
Sprint 2 | Day 16 | Balance not updating | Debugged transaction commit
Sprint 3 | Day 17 | SMTP authentication issue | Reconfigured Gmail SMTP
Sprint 3 | Day 18 | CSV file not generating | Fixed file write path
Sprint 4 | Day 19 | Final UI bugs | Corrected layout and UI issues

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-01-12 | 2025-07-12 | Dharanish | Proper DB planning and entity design | Random coding | Clean layered Coding | Created Account module with REST API
2 | Sprint 2 | 2025-08-12 | 14/12/2025 | Dharanish | Validating transactions (deposit/withdraw) | Hard-coded values | Modular service methods | Implemented Deposit, Withdraw & Transfer
3 | Sprint 3 | 15/12/2025 | 21/12/2025 | Dharanish | Testing frontend and backend together | Skipping validation testing | Using service layer architecture | Integrated frontend with backend and fixed bug
4 | Sprint 4 | 22/12/2025 | 28/12/2025 | Dharanish | End-to-end test case execution | Manual DB modification | UI-based testing | Performed end-to-end test scenarios